## Delivery
Work item | Summary | Original plan | Approved replan | Actual | Status | Dependencies | Owner / discussion
TEAM-10 | Confirm pilot dependency list | 2026-10-21 |  | 2026-10-21 | done |  | Product lead. Submit remains disabled.
TEAM-11 | Restore submit handler | 2026-10-29 |  |  | open | Decision on duplicate submissions | Order Platform Team
TEAM-12 | Connect submission and reservation | 2026-10-30 |  |  | open | TEAM-11 | Fulfilment engineer. No event consumer runs today.
TEAM-13 | Confirm incident handover | 2026-10-30 |  |  | open | Host Operations review | Keep signed boundary ownership until a handover is accepted.
TEAM-14 | Reservation pilot | 2026-11-02 | 2026-11-09 |  | open | TEAM-11; TEAM-12 | TEAM-14 ¦ Reservation pilot ¦ planned 2026-11-02 ¦ approved replan 2026-11-09 ¦ actual blank ¦ open ¦ depends on TEAM-11 submit handler and TEAM-12 event wiring ¦ product lead approved 22 October. This moves the pilot only; it does not claim work is done.
TEAM-15 | Refresh stock seed notes | 2026-10-23 |  | 2026-10-23 | done |  | TEAM-15 ¦ Refresh stock seed notes ¦ planned 2026-10-23 ¦ actual 2026-10-23 ¦ done ¦ no dependencies ¦ fulfilment engineer. Legend: planned is a forecast; actual is completion; blank actual means not completed.
TEAM-16 | Measure shopper interactions | 2026-11-03 |  |  | open | Request timing hook | TEAM-16 ¦ Measure shopper interactions ¦ planned 2026-11-03 ¦ actual blank ¦ open ¦ depends on request timing hook ¦ supports the one-second shopper budget and the selected-shopper release goal ¦ product lead.
TEAM-17 | Arrange dispatch readiness review | 2026-11-12 |  |  | open | Agreement on order-confirmed signal and cancellation handling | TEAM-17 ¦ Arrange dispatch ¦ planned readiness review 2026-11-12 ¦ actual blank ¦ open ¦ depends on agreement of an order-confirmed signal and cancellation handling ¦ Delivery coordinator. This is the stage readiness-review date, not a shipping launch or a completed handover.

## Readme
Planning conventions
Planned means forecast; actual means completed. Blank actual means not completed.
Product lead approved pilot replan on 22 October. Older board copy remains in circulation.
Not a time sheet. Review open dependencies on Monday.